## Sheet1
Initiative Name | Department | Owner | Start Date | Target Date | Status | Key Dependency | Bottleneck | Next Action | Last Updated
Reduce customer response TAT | Support | Ops Lead | 2026-01-01 | 2026-01-31 | At Risk | Tool configuration | Support team bandwidth | Align daily shift allocation | 2026-01-18
Onboard new service providers | Ops | Vendor Manager | 2026-01-05 | 2026-01-25 | Delayed | Document verification | Incomplete submissions | Follow-up with pending vendors | 2026-01-18
Refund process turnaround improvement | Finance | Finance Ops | 2026-01-03 | 2026-01-20 | At Risk | Cross-team approval | Ownership ambiguity | Assign backup approver | 2026-01-18
Weekly leadership reporting cadence | BizOps | Ops Analyst | 2026-01-01 | 2026-01-10 | On Track | Data availability | None | Automate data collection | 2026-01-18
Customer escalation SOP update | Support | QA Lead | 2026-01-07 | 2026-01-22 | On Track | SOP review | None | Circulate for sign-off | 2026-01-18
Internal handoff clarity between teams | Ops | Program Manager | 2026-01-02 | 2026-01-28 | At Risk | Multiple stakeholders | Unclear handoff points | Define RACI ownership | 2026-01-18
New hire onboarding checklist | HR Ops | HR Lead | 2026-01-06 | 2026-01-24 | On Track | Manager inputs | None | Finalize checklist | 2026-01-18
Daily ops metrics dashboard | BizOps | Data Analyst | 2026-01-04 | 2026-01-18 | Delayed | Data pipeline | Inconsistent data sources | Standardize metrics | 2026-01-18
Quality audit readiness checklist | Ops | QA Manager | 2026-01-08 | 2026-01-30 | On Track | SOP alignment | None | Dry run audit | 2026-01-18
Vendor payment reconciliation | Finance | Accounts | 2026-01-05 | 2026-01-21 | At Risk | External confirmation | Dependency delays | Escalate unresolved cases | 2026-01-18
Customer feedback loop closure | Support | CX Lead | 2026-01-10 | 2026-01-31 | On Track | Survey data | None | Weekly review cadence | 2026-01-18
Escalation SLA definition | Ops | Ops Head | 2026-01-12 | 2026-01-26 | At Risk | Leadership sign-off | Approval pending | Align with leadership | 2026-01-18